## PROJECT SCHEDULE
TopCare Auto Repair - Payroll Upgrade
To be completed by: |  | Liliana Varela - Rodriguez
Deadline: |  | 2018-05-11
Green Team Schedule
% done | Phase | Due By | Notes
100% | Setting up communication |  | Setting up Kik (mobile communication) getting familiar with google docs
100% | Assigning Partners/ Subgroups |  | Getting information from group mebers as to who would like to do what. First come first serve.
100% | Business Specifics |  | What type of business are we working with? What areas are they located in? What is the business name?
100% | Subgroup team members 1st brainstorm |  | This was significantly slowed down and took me almost 3 weeks to get everyone finally communicating. Mostly due to schedule interruptions
100% | CHECK POINT!!!! | 2018-05-02 | CREATE YOUR FOLDERS, UPDATE YOUR SUMMARIES AND GRAPHS ¦ These check points will give me a thorough idea of how far along we are in our milestone
100% | MILESTONE 1: First Drafts | 2018-03-07 | Database (list of data entities, graph draft) ¦ Network (monetary estimate, details of hardware, software, etc.) ¦ Presentation (report draft, presentation draft, logo) ¦ SHOULD BE UPLOADED TO YOUR CANVAS FILE
100% | Subgroups discuss research | 2018-03-13 | Continue emailing and contacting each other for more information. If you need any help ask. Please do not wait until the last minute, it's better for all of us if we get a solution fast! This portion should be innitiated by the 13th but continued until the Project.
65% | Review, Research, Rewrite | 2018-03-15 | Use this time to make revisions to your first draft, build your charts, review costs (make sure everything is accounted for don't underestimate costs, but keep them within a reasonable budget).
0% | CHECK POINT!!!! | 2018-03-17 | UPDATE YOUR FILES (SUMMARIES AND DRAFTS)
0% | MILESTONE 2: Second Drafts | 2018-03-19 | PROJECT STATUS REPORT ¦ UPDATE CANVAS FOLDER
0% | Review, Research, Rewrite | 2018-04-09 | Revise your second drafts Database (revise to 3rd NF, revise data flow) ¦ Network (make sure your connection charts make sense and reflect the budget) ¦ Presentation (Include graphs of costs and savings, revise report)
0% | CHECK POINT!!!! | 2018-04-13 | UPDATE YOUR FILES (SUMMARIES AND DRAFTS)
0% | MILESTONE 3: Third Draft | 2018-04-16 | PROJECT STATUS REPORT ¦ UPDATE CANVAS FOLDER
0% | Review, Rewrite | 2018-04-04 | Final revisions (dot your I's and cross your t's, make sure your documentation matches your graphs, provide legible keys to graphs and charts,) ¦ Network and Database (provided summaries that fully describes your charts)
0% | CHECK POINT!!!! | 2018-04-30 | This is a final check, I will set up conferences with each group member (or group) in the following days. We will use this time to go over the final draft.
0% | PowerPoint and Report Review | 2018-05-04 | By this point, the final PowerPoint and Report should be absolutely done (no more revisions). EVERY GROUP MEMBER SHOULD BE AWARE WHAT SLIDES THEY WILL PRESENT
0% | FINAL MILESTONE | 2018-05-11 | TURN IN YOUR FILES AND SLIDES ¦ END OF PROJECT
| END OF PROJECT!!! |  | GREAT JOB, YOU MADE THIS PROJECT HAPPEN!!! BE PROUD

## GANTT CHART
ASSIGNMENT
PHASE 1
The bulk of this phase will be database and network team researching making plans and building the first draft of their chart. Presentation group begins rough draft, logo.
Network begins research and development of charts and plans for connection. Network will meet up with Database to ensure hardware, software, and connections are meeting database needs.
At about a midpoint of Network group's research and development, they will communicate the costs
PHASE 2
This phase will consists of assigning each group and each team member their project duties
Meet Up!
Database
Network
Presentation
Meet Up!
Presentation
PHASE 3
The bulk of this phase will be database and network team researching making plans and building drafts of their chart. Presentation group begins rough draft, logo and taking notes from other groups
Meet Up!
PHASE 4
PHASE 5
Phase 4 will be final touches for both database and network groups. Presentation group will be collecting notes, revising their assignments, and meeting with project guide during this phase
UPDATES FROM AND TO GROUPS
UPDATES FROM AND TO GROUPS
UPDATES FROM AND TO GROUPS
As database and network finish, the bulk of presentaion goup's work begins. They will meet up with each group (if necessary) to take note of any changes.
Project Guide/Lead
PHASE 6
Meet Up!
Meet Up!
SENDS SLIDES TO GROUPS
SENDS SLIDES TO GROUPS
Presentation group will assign every group slides. We will give our portion of the presentation. END OF PROJECT
GIVE PRESENTATION
END OF PROJECT!
03/02 - 03/07
03/07 - 03/19
03/19 - 04/09
04/09 - 04/16
04/16 - 05/04
05/04 - 05/11

## STEPS
EACH GROUP
RECIEVES
ASSIGNMENT
PRESENTATION
DATABASE
NETWORK
PROJECT GUIDE
STEP 2
STEP 1
SET UP COMMUNICATION APPS; BEGIN COMMUNICATION
connected!
connected!
connected!
connected!
STEP 3
BRAINSTORM SESSION: BUSINESS SPECIFICS
STEP 4
FIRST DRAFT UPLOADS
connected!
STEP 5
CONTINUE RESEARCH & COMMUNICATIONS; REVISE YOUR DRAFTS; UPLOAD
STEP 6
STEP 7
HALF-WAY
STEP 8
LAST ROUGH DRAFT
STEP 9
STEP 10
FINAL
COMMUNICATIONS
CONTINUE RESEARCH & COMMUNICATIONS; REVISE YOUR DRAFTS; UPLOAD
CONTINUE RESEARCH & COMMUNICATIONS; REVISE YOUR DRAFTS; UPLOAD
CONTINUE RESEARCH & COMMUNICATIONS; REVISE YOUR DRAFTS; UPLOAD; PRIME TIME FOR HELP
UPDATE FILES;
PROJECT STATUS REPORT
CONTINUE RESEARCH & COMMUNICATIONS; REVISE YOUR DRAFTS; UPLOAD
STEP 11 Presentaion Group
STEP 12
Final Uploads
STEP 13
Presentation Group Assigns Slides
03/02 - 03/07
03/07 -
- 03/19
03/19 - 04/09
STEP 14
Green Team Gives Presentation
END PROJECT
04/09 - 04/16
04/16 - 05/04
CONTINUE RESEARCH & COMMUNICATIONS; REVISE YOUR DRAFTS; UPLOAD; PRIME TIME FOR HELP
PRESENTATION GROUP CONTINUES RESEARCH & COMMUNICATIONS;
REVISE FINAL DRAFTS; ADD FINAL TOUCHES; PRIME TIME FOR HELP
ALL FINAL UPLOADS
05/04
05/11
PRESENTATION GROUP ASSIGNS EVERY GROUP THEIR SLIDES;
EVERY GROUP MEMBER IN CHARGE OF 1 SLIDE
PRESENTATION IS TURNED IN BY GROUP
CONGRATULATIONS!!!!