## Form Responses 1
Timestamp | Untitled Question

## Sheet1
Project Scope Statement
Project Title: | Green Computing Research Project
Date Prepared: | 2018-09-21
Prepared by: Blue Group [Liliana Varela-Rodriguez]
Project Start Date: 10/01/18 | Project Finish Date 04/01/18
Budget Information | The budget for this project is $500,000.
Roles And Responsibilities
Name | Role | Responsibilities
Natalie | VP of Operations | Program Sponsor
Ito |  | Project Manager
Ben | CIO | Project Sponsor
Project Objectives: The main purpose of the Green Computing Research Project is to research possible applications of green computing, including the following: • Data center and overall energy efficiency • Disposal of electronic waste and recycling • Telecommuting • Virtualization of server resources • Thin client solutions • Use of open source software • Development of new software to address green computing for internal use and potential sale to other organizations
Project Justification:
The project is will be able to provide We Are Big, Inc., with an extensive report, including detailed financial analysis and recommendations for which green computing technologies to implement.
Product Characteristics and Requirements:
• The product needs to meet budget guidelines • The product requires approval from stakeholders
Summary of Project Deliverables
• Project management-related deliverables: business case, charter, team contract, scope statement, WBS, schedule, cost baseline, status reprts, final project presentation, final project report, lessons learned report, and any other documentation required to manage the project.
• Project -related deliverables: research reports, design documents, software code, hardware, and etc.
Research green computing projects performed by large organizations and include definition of green computing; Describe each area of green computing with detailed example of how each area has been implimented, investigate the return on investments. Summarize results in short paper and cite at least three references. | Prepare a weighted decision matrix using the template named wtd_decisions_matrix.xls from the companion website. Ben will use this matrix to evaluate applicants for project manager for this importan project; develop at least 5 criteria, assign weights to each criterion, assign scores, and then calculate the weihted scores for four fictitious applicants Print the spreadsheet and bar chart with the results. Write a one page paper that describes the weighted decision matrix and summarizes the results.
Prepare the financial section of a business case for the Green Coputing Research Project. Assume that this project will take six months to complet (in year 0) and will const $5000,000. The xosts to implement some of the technologies willl be $2 million for year one and $600,000 for years two and three. Estimate benefits are $500,000 in the first year after implementation and $2.5 million in the following two years. | Prepare a project charter for the Green Computing Research Project. Again, assume that the project will take six months to complete and that the budget is $500,000.
Because people will request changes to the project, make sure that you have a good integrated change control process in place. You also want to address change requests as quickly as possible. Review the template for a change request for, write a short papter describing plan to manage changes in a timely maner. Explain who will be involved in making change control decisions, what paperwork or electronic systems will be used to collect and respond to changes and other related issues.
Project Success Criteria: