## WBS
Project Work Breakdown Structure
Project Title: | Green Computing Research Project
Date Prepared: | 2018-09-24
Prepared by: | Blue Team
ID# | Activity Name | Estimated Duration (in hours) | Resource (person's name or title) | Predecessor ID# (dependency)
1 | Research Green Computing | 3 Hours | Natalie, Ito, Ben
2 | Summarize Research | 2 Hours | Natalie | 1
3 | Define green computing | >1 Hour | Natalie | 2018-01-02
4 | Desbribe area of green computing | 1.5 Hours | Natalie | 1 - 3
5 | Implimentation examples | 1 Hour | Natalie | 1 - 4
6 | Investment implimentation | 1 Hour | Ben, Natalie | 1 - 5
7 | Create Decision Matrix | 1.5 Hours | Ito | 1 - 6
8 | Evaluate Employees | 2 Hours | Natalie, Ito, Ben | 7
9 | Develop 5 criteria | 2 Hours | Ito
10 | Assign weight for criteria, scores | 1 Hour | Ito
11 | Calculate weighted scores | 1 Hour | Ito | 10
12 | Print spreadsheets, bar charts, results | > 1 Hour | Ito | 11
13 | Description of Matrix and Result summary | 2 Hours | Ito, Ben | 2018-07-12
14 | Financial of Business Case | 2.5 Hours | Natalie, Ben
15 | Calculate NVP, ROI, the year that payback occurs | 2 Hours | Ben
16 | Prepare project Charter | 1.5 Hours | Ben | 14
17 | Select Team | 1 Hour | Ito, Ben | 1 - 15
18 | Integrated change control process | 1.5 Hours | Ito | 2018-11-16
19 | Describe change management | 1 Hour | Natalie | 18